## Order Level
[9 empty] | Non-Standard Colours | Pink |  |  | Estimated = |  | Yellow
[9 empty] | Down-Payment Received | Blue |  |  | Complete = |  | Green
SI No. | PO# | PI | SO | Rev# | Order Status | Date Ordered (PO Date) | Active | Qty of Skids | Stocking Location | Port of Destination | M2 | Standard Colors Only? | All Material Available | Production Begin | Production Complete | Dispatch from Factory | PI DATE | PI Sent? | STATUS | Notes
1 | 52954707 | NX/PI/25/09/972 | RL/NCSO/25/11/9 | 0 | In Production | 2025-10-31 | Yes | 13 | Hillsboro, TX | Houston | 8143.6073 | Yes | Yes | 2025-12-18 | 2025-12-26 | 2025-12-26 |  | Yes | SHIPPED | Back-dated
2 | 24099925 | NX/PI/25/09/968 | RL/NCSO/25/11/4 | 0 | In Production | 2025-11-03 | Yes | 10 | Granger, IN | Baltimore | 7971.735 | Yes | Yes | 2025-12-18 | 2025-12-29 | 2025-12-29 |  | Yes | SHIPPED | Back-dated
3 | 52954705 | NX/PI/25/09/973 | RL/NCSO/25/11/10 | 0 | In Production | 2025-10-31 | Yes | 13 | Hillsboro, TX | Houston | 6232.719 | Yes | Yes | 2025-12-21 | 2025-12-31 | 2025-12-31 |  | Yes | SHIPPED | 0086 (1245*2745 mm) - 450 sheets not shipped - quality issue
4 | 24104813 | NX/PI/25/09/969 | RL/NCSO/25/11/5 | 0 | In Production | 2025-11-03 | Yes | 15 | Granger, IN | Baltimore | 8590.5 | Yes | Yes | 2025-12-24 | 2025-12-31 | 2025-12-31 |  | Yes | SHIPPED
5 | 52954701 | NX/PI/25/09/974 | RL/NCSO/25/11/11 | 0 | In Production | 2025-11-03 | Yes | 14 | Hillsboro, TX | Houston | 8378.1653 | Yes | Yes | 2025-12-28 | 2026-01-09 | 2026-01-08 |  | Yes | SHIPPED
6 | 24104818 | NX/PI/25/09/970 | RL/NCSO/25/11/7 | 0 | In Production | 2025-11-03 | Yes | 15 | Granger, IN | Baltimore | 8590.5 | Yes | Yes | 2025-12-29 | 2026-01-09 | 2026-01-08 |  | Yes | SHIPPED
7 | 24116019 | NX/PI/25/09/971 | RL/NCSO/25/11/8 | 0 | In Production | 2025-11-03 | Yes | 11 | Granger, IN | Baltimore | 8200.068 | Yes | Yes | 2025-12-29 | 2026-01-12 | 2026-01-08 |  | Yes | SHIPPED
8 | 24099911 | NX/PI/25/09/966 | RL/NCSO/25/11/2 | 0 | In Production | 2025-11-03 | Yes | 14 | Granger, IN | Baltimore | 8505.84 | No | Yes | 2025-12-29 | 2026-01-17 | 2026-01-10 |  | Yes | SHIPPED
9 | 52954697 | NX/PI/25/09/975 | RL/NCSO/25/11/13 | 0 | In Production | 2025-11-03 | Yes | 14 | Hillsboro, TX | Houston | 8495.1953 | No | Yes | 2026-01-10 | 2026-01-17 | 2026-01-15 |  | Yes | SHIPPED
10 | 24099879 | NX/PI/25/09/967 | RL/NCSO/25/11/3 | 0 | In Production | 2025-11-03 | Yes | 14 | Granger, IN | Baltimore | 8505.84 | No | Yes | 2026-01-13 | 2026-01-17 | 2026-01-15 |  | Yes | SHIPPED | Replacing Victory Red with Indigo Blue, Victory Red doesn’t need to be shipped again for these orders - Mr. Sarfaraz
11 | 52963984 | NX/PI/25/09/976 | RL/NCSO/25/11/14 | 0 | In Production | 2025-11-04 | Yes | 13 | Hillsboro, TX | Houston | 8494.386 | No | Yes | 2026-01-16 | 2026-01-23 | 2026-01-22 |  | Yes | SHIPPED | Replacing Victory Red with Indigo Blue Victory Red doesn’t need to be shipped again for these orders - Mr. Sarfaraz
12 | 52963980 | NX/PI/25/09/977 | RL/NCSO/25/11/15 | 1 | In Production | 2025-11-04 | Yes | 14 | Hillsboro, TX | Houston | 8982.9862 | No | Yes | 2025-01-20 | 2026-01-23 | 2026-01-22 |  | Yes | SHIPPED | Replace Victory Red with 450 sheets of Charcoal Metallic (2745 mm/108") Victory Red doesn’t need to be shipped again for these orders - Mr. Sarfaraz
13 | 52952099 | NX/PI/25/09/978 | RL/NCSO/25/11/17 | 0 | Proforma Invoice Sent | 2025-11-09 | Yes | 13 | Minneota, MN | Houston | 8429.895 | Yes | Yes | 2026-01-20 | 2026-01-31 | 2026-01-23 |  | Yes | SHIPPED
14 | 24092839 | NX/PI/25/09/979 | RL/NCSO/25/11/18 | 0 | Proforma Invoice Sent | 2025-11-09 | Yes | 14 | Granger, IN | Baltimore | 8505.84 | Yes | Yes | 2026-01-23 | 2026-01-26 | 2026-01-26 |  | Yes | SHIPPED
15 | 24092848 | NX/PI/25/09/980 | RL/NCSO/25/11/19 | 0 | Proforma Invoice Sent | 2025-11-09 | Yes | 14 | Granger, IN | Baltimore | 8505.84 | No | Yes | 2026-01-26 | 2026-02-13 | 2026-02-11 |  | Yes | SHIPPED | Not shipped - Indigo Blue - 400 sheets, Victory Red - 400 sheets ( 1245*2440) Victory Red doesn’t need to be shipped again for these orders - Mr. Sarfaraz
16 | 52970942 | NX/PI/25/08/981 | RL/NCSO/25/11/20 | 0 | Downpayment Received | 2025-11-24 | Yes | 13 | Nampa, ID | Oakland | 7806.15 | Yes | Yes | 2026-02-05 | 2026-02-24 | 2026-02-17 |  | Yes | SHIPPED
17 | 52970945 | NX/PI/25/08/982 | RL/NCSO/25/11/21 | 0 | Downpayment Received | 2025-11-24 | Yes | 13 | Nampa, ID | Oakland | 8255.097 | Yes | Yes | 2026-02-01 | 2026-02-13 | 2026-02-12 |  | Yes | SHIPPED
18 | 52970947 | NX/PI/25/08/983 | RL/NCSO/25/11/22 | 0 | Downpayment Received | 2025-11-24 | Yes | 13 | Nampa, ID | Oakland | 7923.18 | Yes | Yes | 2026-02-17 | 2026-02-24 | 2026-02-17 |  | Yes | SHIPPED
19 | 52970948 | NX/PI/25/08/984 | RL/NCSO/25/11/23 | 0 | Downpayment Received | 2025-11-24 | Yes | 13 | Nampa, ID | Oakland | 8260.824 | Yes | Yes | 2026-02-07 | 2026-02-11 | 2026-02-12 |  | Yes | SHIPPED
23 | 24160596 | NX/PI/26/01/1002 | RL/NCSO/26/01/3 | 0 |  | 2025-12-31 |  |  | Ashburn, GA | Savannah (ASHBURN) | 7461.285 | Yes | Yes | 2026-02-09 | 2026-02-10 | 2026-03-05 |  | Yes | SHIPPED | Awaiting coils 0105 Indigo Blue, 0089 Red
21 | 52971845 | NX/PI/25/09/986 | RL/NCSO/25/11/25 | 0 | Proforma Invoice Sent | 2025-11-24 | Yes | 12 | Minneota, MN | Houston | 8202.06 | Yes | Yes | 2026-02-06 | 2026-02-13 | 2026-02-13 |  | Yes | SHIPPED
24 | 24160605 | NX/PI/26/01/1003 | RL/NCSO/26/01/4 | 0 |  | 2025-12-31 |  |  | Ashburn, GA | Savannah (ASHBURN) | 7461.285 | Yes | Yes | 2026-02-09 | 2026-02-10 | 2026-03-05 |  | Yes | SHIPPED | Awaiting coils 0105 Indigo Blue, 0089 Red
25 | 24160553 | NX/PI/26/01/1004 | RL/NCSO/26/01/5 | 0 |  | 2025-12-31 |  |  | Ashburn, GA | Savannah (ASHBURN) | 7461.285 | Yes | Yes | 2026-02-09 | 2026-02-10 | 2026-03-05 |  | Yes | SHIPPED
26 | 24160610 | NX/PI/26/01/1005 | RL/NCSO/26/01/6 | 0 |  | 2025-12-31 |  |  | Ashburn, GA | Savannah (ASHBURN) | 7461.285 | Yes | Yes | 2026-02-09 | 2026-02-10 | 2026-03-07 |  | Yes | SHIPPED
33 | 24160657 | NX/PI/26/01/992 | RL/NCSO/26/01/9 | 0 |  | 2025-12-31 |  |  | Savannah, GA | Savannah | 8505.84 | Yes | Yes | 2026-03-04 | 2026-03-06 | 2026-03-08 |  | Yes | SHIPPED
31 | 24160667 | NX/PI/26/01/990 | RL/NCSO/26/01/11 | 0 |  | 2025-12-31 |  |  | Savannah, GA | Savannah | 8202.06 | Yes | Yes | 2026-03-07 | 2026-03-09 | 2026-03-14 |  | Yes | SHIPPED
27 | 24160612 | NX/PI/26/01/1006 | RL/NCSO/26/01/7---- EU/NCSO/26/01/190 | 0 |  | 2025-12-31 |  |  | Ashburn, GA | Savannah (ASHBURN) | 7350.48 | Yes | Yes | 2026-02-02 | 2026-02-13 | 2026-02-13 |  | Yes | SHIPPED
28 | 24160600 | NX/PI/26/01/1007 | RL/NCSO/26/01/8---- EU/NCSO/26/01/191 | 0 |  | 2025-12-31 |  |  | Ashburn, GA | Savannah (ASHBURN) | 7350.48 | Yes | Yes | 2026-02-02 | 2026-02-13 | 2026-02-13 |  | Yes | SHIPPED
30 | 24160660 | NX/PI/26/01/989 | RL/NCSO/26/01/12 | 0 |  | 2025-12-31 |  |  | Savannah, GA | Savannah | 8505.84 | Yes | Yes | 2026-03-08 | 2026-03-10 | 2026-03-14 |  | Yes | SHIPPED | Awaiting coils 0105 Indigo Blue, 0089 Red (meant to start production on 16/03/2026 but awaiting coils)
60 | 52996151 | NX/PI/26/01/1025 | RL/NCSO/26/02/19 | 1 |  | 2026-02-03 |  |  | Nampa, ID | Oakland | 7455.06 | Yes | 2026-04-04 | 2026-04-02 | 2026-04-04 | 2026-04-16 | 2025-12-25 | Yes | SHIPPED
44 | 24169135 | NX/PI/26/01/1009 | RL/NCSO/26/01/24 | 0 |  | 2026-01-10 |  |  | Granger, IN | Baltimore | 8202.06 | No | 2026-04-02 | 2026-04-03 | 2026-05-23 | 2026-05-24 |  | Yes | ON HOLD | Part quantity produced
49 | 24174781 | NX/PI/26/01/1014 | RL/NCSO/26/02/6 | 0 |  | 2026-01-20 |  |  | Houston, TX | Houston | 8505.84 | Yes | 2026-04-04 | 2026-04-05 | 2026-04-07 | 2026-04-17 |  | Yes | SHIPPED
29 | 24160651 | NX/PI/26/01/988 | RL/NCSO/26/01/13 | 0 |  | 2025-12-31 |  |  | Savannah, GA | Savannah | 8505.84 | Yes | Yes | 2026-03-01 | 2026-03-03 | 2026-03-07 |  | Yes | SHIPPED
54 | 24174793 | NX/PI/26/01/1019 | RL/NCSO/26/02/11 | 0 |  | 2026-01-20 |  |  | Houston, TX | Houston | 8202.06 | Yes | 2026-04-04 | 2026-04-09 | 2026-04-11 | 2026-05-02 |  | Yes | SHIPPED
37 | 24160669 | NX/PI/26/01/996 | RL/NCSO/26/01/17 | 0 |  | 2025-12-31 |  |  | Savannah, GA | Savannah | 8202.06 | Yes | 2026-04-04 | 2026-04-15 | 2026-04-24 | 2026-05-02 |  | Yes | SHIPPED
47 | 24174777 | NX/PI/26/01/1012 | RL/NCSO/26/02/4 | 0 |  | 2026-01-20 |  |  | Houston, TX | Houston | 8505.84 | Yes | 2026-04-04 | 2026-04-14 | 2026-04-16 | 2026-05-01 |  | Yes | SHIPPED
34 | 24160655 | NX/PI/26/01/993 | RL/NCSO/26/01/14 | 0 |  | 2025-12-31 |  |  | Savannah, GA | Savannah | 8505.84 | Yes | 2026-04-04 | 2026-04-16 | 2026-05-05 | 2026-05-19 |  | Yes | SHIPPED
53 | 24174791 | NX/PI/26/01/1018 | RL/NCSO/26/02/10 | 0 |  | 2026-01-20 |  |  | Houston, TX | Houston | 8202.06 | Yes | 2026-04-04 | 2026-05-12 | 2026-05-17 | 2026-05-23 |  | Yes | SHIPPED | Jurf ( 23.05.2026) 1
32 | 24160671 | NX/PI/26/01/991 | RL/NCSO/26/01/10 | 0 |  | 2025-12-31 |  |  | Savannah, GA | Savannah | 8202.06 | Yes | Yes | 2026-02-24 | 2026-02-27 | 2026-03-08 |  | Yes | SHIPPED
20 | 52970952 | NX/PI/25/08/985 | RL/NCSO/25/11/24 | 0 | Downpayment Received | 2025-11-24 | Yes | 12 | Nampa, ID | Oakland | 8055.399 | No |  | 2026-05-25 | 2026-05-28 | 2026-05-29 |  | Yes | ON HOLD | Regular supplier material will arrive between late May and mid-June
22 | 24143625 | NX/PI/25/12/987 | RL/NCSO/25/12/5 | 0 | Proforma Invoice Sent | 2025-12-03 | Yes | 12 | Granger, IN | Baltimore | 8202.06 | No |  | 2026-05-28 | 2026-05-31 | 2026-06-01 |  | Yes | ON HOLD
43 | 24169131 | NX/PI/26/01/1008 | RL/NCSO/26/01/23 | 1 |  | 2026-01-10 |  |  | Granger, IN | Baltimore | 8202.06 | No |  | 2026-06-01 | 2026-06-03 | 2026-06-04 |  | Yes | ON HOLD
51 | 24174787 | NX/PI/26/01/1016 | RL/NCSO/26/02/8 | 0 |  | 2026-01-20 |  |  | Houston, TX | Houston | 8505.84 | Yes | OLD STOCK | 2026-03-31 | 2026-04-02 | 2026-04-17 |  | Yes | SHIPPED
35 | 24160670 | NX/PI/26/01/994 | RL/NCSO/26/01/15 | 0 |  | 2025-12-31 |  |  | Savannah, GA | Savannah | 8202.06 | Yes | 2026-04-02 | 2026-04-04 | 2026-04-06 | 2026-04-16 |  | Yes | SHIPPED
52 | 24174788 | NX/PI/26/01/1017 | RL/NCSO/26/02/9 | 0 |  | 2026-01-20 |  |  | Houston, TX | Houston | 8505.84 | Yes | 2026-02-08 | 2026-03-22 | 2026-03-29 | 2026-04-11 |  | Yes | SHIPPED | dispatched from factory on 11-04-2026 (Back dated)
56 | 24174796 | NX/PI/26/01/1021 | RL/NCSO/26/02/13 | 0 |  | 2026-01-20 |  |  | Houston, TX | Houston | 8202.06 | Yes | 2026-02-08 | 2026-03-11 | 2026-03-13 | 2026-04-11 |  | Yes | SHIPPED | dispatched from factory on 11-04-2026 (Back dated)
48 | 24174780 | NX/PI/26/01/1013 | RL/NCSO/26/02/5 | 0 |  | 2026-01-20 |  |  | Houston, TX | Houston | 8505.84 | Yes | Yes | 2026-04-15 | 2026-04-30 | 2026-05-02 |  | Yes | SHIPPED
38 | 24160658 | NX/PI/26/01/997 | RL/NCSO/26/01/18 | 0 |  | 2025-12-31 |  |  | Savannah, GA | Savannah | 8505.84 | Yes |  | 2026-05-01 | 2026-05-04 | 2026-06-03 |  | Yes | CONTAINER BOOKED | 03-06-2026 JURF
42 | 24160656 | NX/PI/26/01/1001 | RL/NCSO/26/01/21 | 0 |  | 2025-12-31 |  |  | Savannah, GA | Savannah | 8505.84 | Yes |  | 2026-05-16 | 2026-05-20 | 2026-06-03 |  | Yes | UNDER PRODUCTION | 03-06-2026 JURF
57 | 24174797 | NX/PI/26/01/1022 | RL/NCSO/26/02/14 | 0 |  | 2026-01-20 |  |  | Houston, TX | Houston | 8197.578 | Yes |  | 2026-05-13 | 2026-05-20 | 2026-05-23 |  | Yes | SHIPPED | Jurf ( 23.05.2026) 1 (black coil - 314.24 m2 short
41 | 24160677 | NX/PI/26/01/1000 | RL/NCSO/26/01/22 | 0 |  | 2025-12-31 |  |  | Savannah, GA | Savannah | 8197.578 | Yes | Yes | 2026-04-27 | 2026-05-10 | 2026-05-19 |  | Yes | SHIPPED
39 | 24160659 | NX/PI/26/01/998 | RL/NCSO/26/01/19 | 0 |  | 2025-12-31 |  |  | Savannah, GA | Savannah | 8505.84 | Yes | Yes | 2026-04-19 | 2026-04-22 | 2026-05-01 |  | Yes | SHIPPED
46 | 24174773 | NX/PI/26/01/1011 | RL/NCSO/26/02/3 | 0 |  | 2026-01-20 |  |  | Houston, TX | Houston | 8505.84 | Yes | 2026-04-02 | 2026-04-03 | 2026-04-05 | 2026-04-17 |  | Yes | SHIPPED
55 | 24174794 | NX/PI/26/01/1020 | RL/NCSO/26/02/12 | 0 |  | 2026-01-20 |  |  | Houston, TX | Houston | 8202.06 | Yes | 2026-02-08 | 2026-03-14 | 2026-03-16 | 2026-04-11 |  | Yes | SHIPPED | dispatched from factory on 11-04-2026 (Back dated)
40 | 24160674 | NX/PI/26/01/999 | RL/NCSO/26/01/20 | 0 |  | 2025-12-31 |  |  | Savannah, GA | Savannah | 8197.578 | Yes |  | 2026-05-15 | 2026-05-20 | 2026-05-22 |  | Yes | SHIPPED | Jurf ( 22.05.2026) 1
36 | 24160661 | NX/PI/26/01/995 | RL/NCSO/26/01/16 | 0 |  | 2025-12-31 |  |  | Savannah, GA | Savannah | 8505.84 | Yes | Yes | 2026-04-17 | 2026-04-19 | 2026-05-01 |  | Yes | SHIPPED
50 | 24174783 | NX/PI/26/01/1015 | RL/NCSO/26/02/7 | 0 |  | 2026-01-20 |  |  | Houston, TX | Houston | 8505.84 | Yes | 2026-02-08 | 2026-03-13 | 2026-03-15 | 2026-04-11 |  | Yes | SHIPPED | dispatched from factory on 11-04-2026 (Back dated)
45 | 24174768 | NX/PI/26/01/1010 | RL/NCSO/26/02/2 | 0 |  | 2026-01-20 |  |  | Houston, TX | Houston | 8505.84 | Yes | 2026-02-08 | 2026-03-23 | 2026-03-26 | 2026-04-11 |  | Yes | SHIPPED | dispatched from factory on 11-04-2026 (Back dated)
58 | 24174799 | NX/PI/26/01/1023 | RL/NCSO/26/02/15 | 0 |  | 2026-01-20 |  |  | Houston, TX | Houston | 8197.578 | Yes | Yes | 2026-04-20 | 2026-05-08 | 2026-05-18 |  | Yes | SHIPPED
59 | 52990927 | NX/PI/26/01/1024 | RL/NCSO/26/02/16 | 0 |  | 2026-01-28 |  |  | Hillsboro, TX | Houston | 7537.0433 | No |  | 2026-05-19 | 2026-05-22 | 2026-05-23 | 2026-02-10 | Yes
61 | 52996157 | NX/PI/26/01/1026 | RL/NCSO/26/02/20 | 0 |  | 2026-02-03 |  |  | Nampa, ID | Oakland | 8138.565 | Yes | Yes | 2026-04-23 | 2026-04-25 | 2026-05-18 | 2026-01-15 | Yes | SHIPPED
62 | 52996236 | NX/PI/26/01/1027 | RL/NCSO/26/02/21 | 0 |  | 2026-02-03 |  |  | Nampa, ID | Oakland | 8062.62 | No |  | 2026-05-24 | 2026-05-27 | 2026-05-28 | 2026-02-15 | Yes
63 | 53000257 | NX/PI/26/01/1028 | RL/NCSO/26/02/22 | 0 | 46063 | 2026-02-10 | 14 | Twin Falls, ID | Twin Falls, ID | Oakland | 8505.84 | Yes |  | 2026-05-14 | 2026-05-20 | 2026-06-03 | 2026-02-05 | Yes | UNDER PRODUCTION | WHITE 03-06-2026 JURF
64 | 53000258 | NX/PI/26/01/1029 | RL/NCSO/26/02/23 | 0 | 46063 | 2026-02-10 | 12 | Twin Falls, ID | Twin Falls, ID | Oakland | 8202.06 | Yes |  | 2026-05-15 | 2026-05-21 | 2026-06-03 | 2026-02-06 | Yes | UNDER PRODUCTION | WHITE 03-06-2026 HAMRIYAH
65 | 53000259 | NX/PI/26/01/1030 | RL/NCSO/26/02/24 | 0 | 46063 | 2026-02-10 | 14 | Twin Falls, ID | Twin Falls, ID | Oakland | 8017.8 | Yes |  | 2026-05-14 | 2026-05-29 | 2026-06-03 | 2026-02-05 | Yes | UNDER PRODUCTION | 03-06-2026 JURF
66 | 53000260 | NX/PI/26/01/1031 | RL/NCSO/26/02/25 | 0 | 46063 | 2026-02-10 | 13 | Twin Falls, ID | Twin Falls, ID | Oakland | 7910.73 | Yes | Yes | 2026-04-25 | 2026-04-27 | 2026-06-03 | 2026-01-17 | Yes | CONTAINER BOOKED | 03-06-2026 JURF
67 | 53000261 | NX/PI/26/01/1032 | RL/NCSO/26/02/26 | 0 | 46063 | 2026-02-10 | 13 | Twin Falls, ID | Twin Falls, ID | Oakland | 7910.73 | Yes | Yes | 2026-04-22 | 2026-04-24 | 2026-05-19 | 2026-01-14 | Yes | SHIPPED
68 | 53000262 | NX/PI/26/01/1033 | RL/NCSO/26/02/27 | 0 | 46063 | 2026-02-10 | 13 | Twin Falls, ID | Twin Falls, ID | Oakland | 7910.73 | Yes |  | 2026-06-05 | 2026-06-08 | 2026-06-09 | 2026-02-27 | Yes
69 | 24190749 | NX/PI/26/01/1034 | RL/NCSO/26/02/28 | 0 | 46063 | 2026-02-10 | 13 | Ashburn, GA | Ashburn, GA | Savannah | 7461.285 | Yes |  | 2026-05-15 | 2026-05-22 | 2026-06-03 | 2026-02-06 | Yes | UNDER PRODUCTION | 03-06-2026 HAMRIYAH
70 | 24190757 | NX/PI/26/01/1035 | RL/NCSO/26/02/29 | 1 | 46063 | 2026-02-10 | 13 | Ashburn, GA | Ashburn, GA | Savannah | 8331.54 | Yes |  | 2026-06-11 | 2026-06-14 | 2026-06-15 | 2026-03-05 | Yes
71 | 24190763 | NX/PI/26/01/1036 | RL/NCSO/26/02/30 | 0 | 46063 | 2026-02-10 | 13 | Ashburn, GA | Ashburn, GA | Savannah | 7350.48 | Yes |  | 2026-05-10 | 2026-05-14 | 2026-06-03 | 2026-02-01 | Yes | PRODUCTION COMPLETE | 03-06-2026 HAMRIYAH
72 | 52998960 | NX/PI/26/01/1037 | RL/NCSO/26/02/31 | 0 | 46063 | 2026-02-10 | 14 | Nampa, ID | Nampa, ID | Oakland | 8705.04 | No |  | 2026-06-17 | 2026-06-20 | 2026-06-21 | 2026-03-11 | Yes
73 | 52999837 | NX/PI/26/01/1038 | RL/NCSO/26/02/32 | 0 | 46063 | 2026-02-10 | 13 | Nampa, ID | Nampa, ID | Oakland | 8021.535 | Yes |  | 2026-06-20 | 2026-06-23 | 2026-06-03 | 2026-03-14 | Yes | UNDER PRODUCTION | WHITE 03-06-2026 JURF
74 | 52999845 | NX/PI/26/01/1039 | RL/NCSO/26/02/33 | 0 | 46063 | 2026-02-10 | 13 | Nampa, ID | Nampa, ID | Oakland | 8021.535 | Yes |  | 2026-06-23 | 2026-06-26 | 2026-06-03 | 2026-03-17 | Yes | UNDER PRODUCTION | WHITE 03-06-2026 JURF
75 | 52999849 | NX/PI/26/01/1040 | RL/NCSO/26/02/34 | 0 | 46063 | 2026-02-10 | 13 | Nampa, ID | Nampa, ID | Oakland | 8021.535 | Yes |  | 2026-06-26 | 2026-06-29 | 2026-06-30 | 2026-03-20 | Yes
76 | 52999869 | NX/PI/26/01/1041 | RL/NCSO/26/02/35 | 0 | 46063 | 2026-02-10 | 13 | Nampa, ID | Nampa, ID | Oakland | 8021.535 | Yes |  | 2026-06-29 | 2026-07-02 | 2026-07-03 | 2026-03-23 | Yes
77 | 52999872 | NX/PI/26/01/1042 | RL/NCSO/26/02/36 | 0 | 46063 | 2026-02-10 | 13 | Nampa, ID | Nampa, ID | Oakland | 8021.535 | Yes | Yes | 2026-04-23 | 2026-04-26 | 2026-06-03 | 2026-01-15 | Yes | CONTAINER BOOKED | 03-06-2026 JURF
78 | 52999875 | NX/PI/26/01/1043 | RL/NCSO/26/02/37 | 0 | 46063 | 2026-02-10 | 13 | Nampa, ID | Nampa, ID | Oakland | 8021.535 | Yes |  | 2026-05-09 | 2026-05-12 | 2026-05-22 | 2026-01-31 | Yes | SHIPPED | 23-05-2026 ( Jurf) 1
79 | 52999878 | NX/PI/26/01/1044 | RL/NCSO/26/02/38 | 0 | 46063 | 2026-02-10 | 13 | Nampa, ID | Nampa, ID | Oakland | 8021.535 | Yes |  | 2026-07-05 | 2026-07-08 | 2026-07-09 | 2026-03-29 | Yes
80 | 52999884 | NX/PI/26/01/1045 | RL/NCSO/26/02/39 | 0 | 46063 | 2026-02-10 | 13 | Nampa, ID | Nampa, ID | Oakland | 8021.535 | Yes |  | 2026-07-08 | 2026-07-11 | 2026-07-12 | 2026-04-01 | Yes
81 | 52999889 | NX/PI/26/01/1046 | RL/NCSO/26/02/40 | 0 | 46063 | 2026-02-10 | 13 | Nampa, ID | Nampa, ID | Oakland | 8278.005 | No |  | 2026-07-11 | 2026-07-14 | 2026-07-15 | 2026-04-04 | Yes
82 | 24189318 | NX/PI/26/01/1047 | RL/NCSO/26/02/41 | 0 | 46063 | 2026-02-10 | 12 | Gordon, PA | Gordon, PA | Baltimore | 7898.28 | Yes |  | 2026-07-14 | 2026-07-17 | 2026-07-18 | 2026-04-07 | Yes
83 | 52996502 | NX/PI/26/01/1048 | RL/NCSO/26/02/42 | 0 | 46063 | 2026-02-10 | 14 | Hillsboro, TX | Hillsboro, TX | Houston | 8229.8858 | No |  | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-04-10 | Yes
84 | 24202598 | NX/PI/26/02/1049 | RL/NCSO/26/02/46 | 0 |  | 2026-02-20 |  |  | Gordon, PA | Baltimore | 8505.84 | Yes |  | 2026-07-20 | 2026-07-23 | 2026-07-24 | 2026-04-13 | Yes
85 | 24202599 | NX/PI/26/02/1050 | RL/NCSO/26/02/47 | 0 |  | 2026-02-20 |  |  | Gordon, PA | Baltimore | 8505.84 | Yes |  | 2026-07-23 | 2026-07-26 | 2026-07-27 | 2026-04-16 | Yes
86 | 24202600 | NX/PI/26/02/1051 | RL/NCSO/26/02/48 | 0 |  | 2026-02-20 |  |  | Gordon, PA | Baltimore | 8202.06 | Yes |  | 2026-07-26 | 2026-07-29 | 2026-07-30 | 2026-04-19 | Yes
87 | 24202605 | NX/PI/26/02/1052 | RL/NCSO/26/02/49 | 0 |  | 2026-02-20 |  |  | Gordon, PA | Baltimore | 8202.06 | Yes |  | 2026-07-29 | 2026-08-01 | 2026-08-02 | 2026-04-22 | Yes
88 | 24202656 | NX/PI/26/02/1053 | RL/NCSO/26/02/50 | 0 |  | 2026-02-20 |  |  | Gordon, PA | Baltimore | 8505.84 | Yes |  | 2026-08-01 | 2026-08-04 | 2026-08-05 | 2026-04-25 | Yes
89 | 24202686 | NX/PI/26/02/1054 | RL/NCSO/26/02/51 | 1 |  | 2026-02-20 |  |  | Gordon, PA | Baltimore | 8505.84 | No |  | 2026-08-04 | 2026-08-07 | 2026-08-08 | 2026-04-28 | Yes
90 | 24202721 | NX/PI/26/02/1055 | RL/NCSO/26/02/52 | 1 |  | 2026-02-20 |  |  | Gordon, PA | Baltimore | 8505.84 | No |  | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-05-01 | Yes
91 | 24202860 | NX/PI/26/02/1056 | RL/NCSO/26/02/53 | 0 |  | 2026-02-20 |  |  | South Paris, ME | Baltimore | 8202.06 | Yes |  | 2026-08-10 | 2026-08-13 | 2026-08-14 | 2026-05-04 | Yes
92 | 53004426 | NX/PI/26/02/1057 | RL/NCSO/26/02/54 | 0 |  | 2026-02-20 |  |  | Hillsboro, TX | Houston | 8087.6445 | No |  | 2026-08-13 | 2026-08-16 | 2026-08-17 | 2026-05-07 | Yes
93 | 24199456 | NX/PI/26/02/1058 | RL/NCSO/26/02/55 | 0 |  | 2026-02-20 |  |  | Gordon, PA | Baltimore | 8505.84 | Yes |  | 2026-08-16 | 2026-08-19 | 2026-08-20 | 2026-05-10 | Yes
94 | 24202634 | NX/PI/26/02/1059 | RL/NCSO/26/02/57 | 1 |  | 2026-02-23 |  |  | Gordon, PA | Baltimore | 8202.06 | No |  | 2026-08-19 | 2026-08-22 | 2026-08-23 | 2026-05-13 | Yes
95 | 24202873 | NX/PI/26/02/1060 | RL/NCSO/26/02/56 | 0 |  | 2026-02-23 |  |  | South Paris, ME | Baltimore | 8505.84 | Yes |  | 2026-08-22 | 2026-08-25 | 2026-08-26 | 2026-05-16 | Yes
96 | 24202608 | NX/PI/26/02/1061 | RL/NCSO/26/02/58 | 1 |  | 2026-02-23 |  |  | Gordon, PA | Baltimore | 8278.005 | No |  | 2026-08-25 | 2026-08-28 | 2026-08-29 | 2026-05-19 | Yes
97 | 24272114 | NX/PI/26/03/1062 |  | 0 |  | 2026-03-18 |  |  | Granger, IN | Savannah | 7909.734 | Yes |  | 2026-08-28 | 2026-08-31 | 2026-09-01 | 2026-05-22 | No
98 | 24272103 | NX/PI/26/03/1063 |  | 0 |  | 2026-03-18 |  |  | Granger, IN | Houston | 8027.76 | Yes |  | 2026-08-31 | 2026-09-03 | 2026-09-04 | 2026-05-25 | No
99 | 53036815 | NX/PI/26/03/1064 |  | 0 |  | 2026-03-18 |  |  | Minneota, MN | Houston | 8278.005 | Yes |  | 2026-09-03 | 2026-09-06 | 2026-09-07 | 2026-05-28 | No
100 | 53036803 | NX/PI/26/03/1065 |  | 0 |  | 2026-03-18 |  |  | Nampa, ID | Oakland | 8366.4 | Yes |  | 2026-09-06 | 2026-09-09 | 2026-09-10 | 2026-05-31 | No
101 | 24272132 | NX/PI/26/03/1066 |  | 0 |  | 2026-03-18 |  |  | South Paris, ME | Baltimore | 8505.84 | Yes |  | 2026-09-09 | 2026-09-12 | 2026-09-13 | 2026-06-03 | No
102 | 24272121 | NX/PI/26/03/1067 |  | 0 |  | 2026-03-18 |  |  | Granger, IN | Baltimore | 7971.735 | Yes |  | 2026-09-12 | 2026-09-15 | 2026-09-16 | 2026-06-06 | No
103 | 53036808 | NX/PI/26/03/1068 |  | 0 |  | 2026-03-18 |  |  | Hillsboro, TX | Houston | 8130.846 | Yes |  | 2026-09-15 | 2026-09-18 | 2026-09-19 | 2026-06-09 | No
104 | 53036798 | NX/PI/26/03/1069 |  | 0 |  | 2026-03-18 |  |  | Twin Falls, ID | Oakland | 8050.17 | Yes |  | 2026-09-18 | 2026-09-21 | 2026-09-22 | 2026-06-12 | No
105 | 24272100 | NX/PI/26/03/1070 |  | 0 |  | 2026-03-18 |  |  | Granger, IN | Baltimore | 8505.84 | Yes |  | 2026-09-21 | 2026-09-24 | 2026-09-25 | 2026-06-15 | No |  | Revised
106 | 53013961 | NX/PI/26/03/1071 |  | 1 |  | 2026-03-18 |  |  | Minneota, MN | Houston | 8202.06 | Yes |  | 2026-09-24 | 2026-09-27 | 2026-09-28 | 2026-06-18 | No
107 | 53014919 | NX/PI/26/03/1072 |  | 0 |  | 2026-03-18 |  |  | Nampa, ID | Oakland | 7455.06 | No |  | 2026-09-27 | 2026-09-30 | 2026-10-01 | 2026-06-21 | No
108 | 53016427 | NX/PI/26/03/1073 |  | 0 |  | 2026-03-18 |  |  | Hillsboro, TX | Houston | 8201.562 | Yes |  | 2026-09-30 | 2026-10-03 | 2026-10-04 | 2026-06-24 | No
109 | 53016422 | NX/PI/26/03/1074 |  | 0 |  | 2026-03-18 |  |  | Hillsboro, TX | Houston | 7974.225 | Yes |  | 2026-10-03 | 2026-10-06 | 2026-10-07 | 2026-06-27 | No
110 | 53016418 | NX/PI/26/03/1075 |  | 0 |  | 2026-03-18 |  |  | Hillsboro, TX | Houston | 8277.507 | Yes |  | 2026-10-06 | 2026-10-09 | 2026-10-10 | 2026-06-30 | No
111 | 53016428 | NX/PI/26/03/1076 |  | 0 |  | 2026-03-18 |  |  | Hillsboro, TX | Houston | 8242.647 | No |  | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-07-03 | No
112 | 53016435 | NX/PI/26/03/1077 |  | 0 |  | 2026-03-18 |  |  | Hillsboro, TX | Houston | 7363.677 | No |  | 2026-10-12 | 2026-10-15 | 2026-10-16 | 2026-07-06 | No
113 | 24233947 | NX/PI/26/03/1078 |  | 0 |  | 2026-03-25 |  |  | Gordon, PA | Baltimore | 8017.8 | Yes |  | 2026-10-15 | 2026-10-18 | 2026-10-19 | 2026-07-09 | No
114 | 53022400 | NX/PI/26/04/1079 |  | 0 |  | 2026-03-31 |  |  | Minneota, MN | Houston | 8505.84 | Yes |  | 2026-10-18 | 2026-10-21 | 2026-10-22 | 2026-07-12 | No
115 | 53023614 | NX/PI/26/04/1080 |  | 0 |  | 2026-04-03 |  |  | Hillsboro, TX | Houston | 8103.207 | No |  | 2026-10-21 | 2026-10-24 | 2026-10-25 | 2026-07-15 | No
116 | 53023619 | NX/PI/26/04/1081 |  | 0 |  | 2026-04-03 |  |  | Hillsboro, TX | Houston | 8191.104 | Yes |  | 2026-10-24 | 2026-10-27 | 2026-10-28 | 2026-07-18 | No
117 | 53036679 | NX/PI/26/05/1082 |  | 0 |  | 2026-05-07 |  |  | Granger, IN | Baltimore | 8505.84 | Yes |  | 2026-10-27 | 2026-10-30 | 2026-10-31 | 2026-07-21 | No
118 | 53036684 | NX/PI/26/05/1083 |  | 0 |  | 2026-05-07 |  |  | Minneota, MN | Houston | 8505.84 | Yes |  | 2026-10-31 | 2026-11-02 | 2026-11-03 | 2026-07-25 | No
119 | 53036682 | NX/PI/26/05/1084 |  | 0 |  | 2026-05-07 |  |  | Minneota, MN | Houston | 8505.84 | Yes |  | 2026-11-02 | 2026-11-05 | 2026-11-06 | 2026-07-27 | No
120 | 53036685 | NX/PI/26/05/1085 |  | 0 |  | 2026-05-07 |  |  | Minneota, MN | Houston | 8505.84 | Yes |  | 2026-11-05 | 2026-11-08 | 2026-11-09 | 2026-07-30 | No
Formulas:
PI DATE = [Production Begin]-(14*7)
Dispatch from Factory = [Yellow]+1